## Sheet
ID | Original iD | Description | Comments SUPPLIER XYZ | Comments Stakeholder | Status SUPPLIER XYZ | Status Stakeholder | Next action responsible | Responsibility To Review | Type | Document name
REQ_001 | NAV_03 | For each feature, the supplier must provide documents explaining the functional architecture. This architecture must be compliant with the DronNav constraints. SLAM constraints: With supplier Obstacle Detection and Mapping Milestone: Kickoff | [2024-05-29 SYS Drone A]: Extrinsic calibration is not performed by SUPPLIER XYZ. Please confirm "calibrate the COMPONENT" indicates extrinsic calibration /intrinsic calibration | 20/05/2024_RM: Already accepted in conformity matrix. Please update the status. 01/08/2024_RM : To be verified if this is referring to Extrinsic or Intrisic calibration. | Rejected | In Progress |  | SYS_DRONES, PM, CAQE | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_002 | SENS_06 | The supplier must send the interface needed for all the features for the autonomous drone navigation system. Milestone: Kickoff | [2024-05-28 SYS Drone A] ; Comments on behalf of PM "- Template refers to COMAPNY A not COMPANY A - Project reference is "Sharing of secret algorithms of COMAPNY ASA" If the intention is to agree the NDA template, then we need latest version and review it with our legal department." | 20/05/2024_RM: Already accepted in conformity matrix. Please update the status. 01/08/2024_RM : To be verified internally. DIAG8a and DIAG8b is not applicable. | Rejected | In Progress |  | SYS_DRONES, SW_DRONES, PM | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_003 | AV-DRFC-FUSE-0015 | The sensor fusion supplier must provide documents detailing the requirements for each sensor to achieve the desired fusion performance in the Autonomous Drone Navigation System. Milestone: Kickoff | [PR_DRONE_AA_2024_04_18] Based on SQM01_20417_23_00968_GEED_DRONESthe requirement is not applicable, requirement is for connector harness - SUPPLIER XYZ is not responsible for harness/wire | 25/04/2024_HA :Not applicable for drone no crimped wire terminal inside the drone | Not applicable | Closed |  | PM, Mfg_drone, ME_DRONES | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_003 B | PERF_12 | Each individual sensor supplier must provide all the data required for complete sensor fusion as requested by the fusion supplier for the Autonomous Drone Navigation System. | [PR_DRONE_AA_2024_04_18] NM41 not applicable- drone will be mounted behind the bumper (location code: CV2), not exposed for external shots. | 02/05/2024_HA : this requirement is not applicable because the drone is mounted behind the bumper is not exposed to for external shots and agreed in comformity matrix | Not applicable | Closed |  | EE_DRONES, ME_DRONES, PM | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_004 | PERF_09 | The FUSION function for the the Autonomous Drone Navigation System shall be fully operational as soon as the system enters standard operation mode. Milestone: Kickoff | [PR_DRONE_AA_2024_04_17] Not applicable based on SQM01, drone is one part product. | 16/05/2024_HA : drone is one part so this requirement is not applicable 20/05/2024_RM: Not Applicable. | Not applicable | Closed |  | ME_DRONES, SYS_DRONES | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_200 | MAPPING_04 | The Autonomous Drone Navigation System shall maintain a minimum update rate of 10 Hz for sensor fusion and navigation data processing. | [PR_DRONE_AA_2024_04_17] Not applicable based on SQM01, drone is one part product. | 16/05/2024_HA : drone is one part so this requirement is not applicable 20/05/2024_RM: Not Applicable. | Not applicable | Closed |  | ME_DRONES, SYS_DRONES | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_005 B | MAPPING_02 | The system shall provide obstacle detection and avoidance capabilities for objects with a minimum size of 0.5m x 0.5m x 0.5m at a distance of up to 50 meters. Comment:This requirement ensures safety by detecting and avoiding potential collisions. Milestone: Kickoff | [PR_DRONE_AA_2024_04_17] SUPPLIER XYZ does not participate in vehicle level simulations nor prepares additional relevant data. CAD is prepared for each mechanical delivery and additional support can be discussed. MESH files is additional costs. | 23/05/2024_HA : SUPPLIER XYZ can provide mesh as plus additional paid services if requested 25/04/2024_HA : SUPPLIER XYZ rejected this requirement because there not particpated in vehicle level simulation, if COMPANY Awant this requiement a FETE must be sent to SUPPLIER XYZ;TBC internally | Not applicable | In Progress |  | ME_DRONES, PM | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_201 | CTRL_07 | The navigation system shall maintain positional accuracy within 1 meter in open areas with clear GPS signals and within 2 meters in GPS-denied environments using SLAM. Comment:This ensures reliable positioning across various | [PR_DRONE_AA_2024_04_17] SUPPLIER XYZ does not participate in vehicle level simulations nor prepares additional relevant data. CAD is prepared for each mechanical delivery and additional support can be discussed. MESH files is additional costs. | 23/05/2024_HA : SUPPLIER XYZ can provide mesh as plus additional paid services if requested 25/04/2024_HA : SUPPLIER XYZ rejected this requirement because there not particpated in vehicle level simulation, if COMPANY Awant this requiement a FETE must be sent to SUPPLIER XYZ;TBC internally | Not applicable | In Progress |  | ME_DRONES, PM | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_201 | ADAS-UAVP22-05(1) | The navigation system shall maintain positional accuracy within 1 meter in open areas with clear GPS signals and within 2 meters in GPS-denied environments using SLAM. Comment:This ensures reliable positioning across various operating conditions. | [PR_DRONE_AA_2024_04_17] Not applicable - no sub-assembly in DRONES. | 16/05/2024_HA : NOT applicable , there no sub-assembly in the drone | Not applicable | Closed |  | EE_DRONES, ME_DRONES | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_006 | AU_02 | The system shall support autonomous flight planning and execution for missions with a maximum duration of 4 hours and a range of up to 50 kilometers. Comment: This defines the operational capabilities of the drone for extended missions. Milestone: Kickoff | [PR_DRONE_AA_2024_04_18] N/A - no stylistic parts | 16/05/2024_HA : SUPPLIER XYZ confirm that there is no stylistic parts so it's not applicable | Not applicable | Closed |  | EE_DRONES, ME_DRONES, PM | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_007 | MAPPING_05 | The system shall be capable of operating in wind speeds up to 15 m/s (54 km/h or 33.5 mph) and compensate for wind effects on flight path and stability. Comment:This requirement ensures the drone can navigate effectively in various weather conditions. | [PR_DRONE_AA_2024_04_17] It need to be defined exactly what is needed, I cant approve without details. | 23/05/2024_HA : SUPPLIER XYZ will check with the SYS team 02/05/2024_HA : SUPPLIER XYZ will check with aftersales | Rejected | In Progress |  | PM, SYS_DRONES | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_008 | CALI_03 | The system shall be capable of operating in wind speeds up to 15 m/s (54 km/h or 33.5 mph) and compensate for wind effects on flight path and stability. Milestone: Kickoff | [PR_DRONE_AA_2024_04_17] SUPPLIER XYZ does not participate in vehicle level simulations nor prepares additional relevant data. CAD is prepared for each mechanical delivery and additional support can be discussed. MESH files is additional costs. Rejected | 23/05/2024_HA : SUPPLIER XYZ can provide mesh as plus additional paid services if requested 25/04/2024_HA : SUPPLIER XYZ rejected this requirement because there not particpated in vehicle level simulation, if COMPANY Awant this requiement a FETE must be sent to SUPPLIER XYZ;TBC internally | Rejected | In Progress |  | ME_DRONES, PM | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_202 | CALI_03 | The Autonomous Drone Navigation System shall utilize data from multiple sensor types including, but not limited to, GPS, IMU, cameras, and LiDAR. The fusion algorithm shall compensate for individual sensor weaknesses by leveraging the strengths of complementary sensors. Milestone: Kickoff | [PR_DRONE_AA_2024_04_18] Not Applicable. No washing / drying requirements on the drone. drone design is covered by IP level defined. | 23/05/2024_HA : TBC with expert 25/04/2024_HA : TBC with the Expert drone is protected against water IP69K | Not applicable | In Progress |  | ME_DRONES | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_009 | AV-SPPC-NAV 38 | The system shall be capable of autonomous recalibration of sensor fusion parameters in flight, adapting to changing environmental conditions or sensor performance degradation. The recalibration process shall not interrupt normal flight operations | [PR_DRONE_AA_2024_04_18] Not Applicable. No washing / drying requirements on the drone. drone design is covered by IP level defined. | 23/05/2024_HA: TBC with the expert 25/04/2024_HA : TBC with the Expert drone is protected against water IP69K | Not applicable | In Progress |  | ME_DRONES | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_010 | AV-DRFC-FUSE-0018 | In the event of a critical sensor failure, the system shall automatically switch to a degraded mode of operation, utilizing remaining functional sensors to maintain basic navigation capabilities. The system shall immediately alert the operator of this change in operational status. Milestone: RFQ Comment about deliverable:This requirement ensures fail-safe operation and transparent communication of system status to the operator. | [PR_DRONE_AA_2024_04_18] Based on SQM01_20417_23_00968_GEED_DRONESthe requirement is not applicable, requirement is for connector harness - SUPPLIER XYZ is not responsible for harness/wire | 06/06/2024_HA : Requirements that are related to harness connector in SQM 01 are not applicable because harness connector was chosen by Stellantis 25/04/2024_HA : SQM01 based on previous Status from RFQ said that is not Applicable and SUPPLIER XYZ is not responsible for connector harness TBC internally | Not applicable | Closed |  | PM, ME_DRONES, EE_DRONES, SYS_DRONES, CAQE, HWQA, PTV_drone | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_013 | FUSION_09 | The Autonomous Drone Navigation System shall use a right-handed coordinate system with the origin at the drone's center of gravity. The X-axis shall point forward, the Y-axis to the right, and the Z-axis downward.Comment about deliverable:This standardized coordinate system ensures consistency in object tracking and navigation calculations. | 23/05/2024_HA : Connector pedharnes has no terminals crim [PR_DRONE_AA_2024_04_18] Based on SQM01_20417_23_00968_GEED_DRONESthe requirement is not applicable, requirement is for connector harness - SUPPLIER XYZ is not responsible for harness/wire MFG_DRONES_L.SIEMBIDA_09-05-24: Not applicable for drone MFG process | 06/06/2024_HA : Requirements that are related to harness connector in SQM 01 are not applicable because harness connector was chosen by Stellantis 23/05/2024_HA : Connector pedharnes has no terminals crim 02/05/2024_HA : SQM01 based on previous Status from RFQ said that is not Applicable and SUPPLIER XYZ is not responsible for connector harness TBC internally | Not applicable | Closed |  | PM, Mfg_drone, ME_DRONES | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_014 | FUSION_11 | The system shall fuse data from multiple sensors (cameras, LiDAR, and drone) to detect and classify objects in the drone's environment with a minimum detection range of 100 meters. Comment about deliverable: Multi-sensor fusion improves detection accuracy and range. During RFQ and for kick off meeting: supplier conformity commitment During development: conformity validated | [2024/03/26] The document DIAGFR5 has been cancelled based on "DML_00123_45_6677_DML_DRONES-2026.xlsx" (version 10.0) from the original .zip file package. | 27/03/2024_RM : To be verified. 01/08/2024_RM : Not Applicable. Closed. | Not applicable | Closed |  |  | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_015 | SENS_04 | The object detection system shall classify objects into at least the following categories: other aircraft, birds, buildings, terrain features, and moving ground vehicles..Comment about deliverable:Accurate classification is crucial for appropriate response and collision avoidance Frequent updates enable timely decision-making for collision avoidance. During RFQ and for kick off meeting: supplier conformity commitment During development: conformity validated | [2024/03/26] The document DIAGCR5 has been cancelled based on "DML_00123_45_6677_DML_DRONES-2026.xlsx" (version 10.0) from the original .zip file package. | 27/03/2024_RM : To be verified. 01/08/2024_RM : Not Applicable. Closed. | Not applicable | Closed |  |  | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_019 | OBS_05 | The system shall track detected objects, providing updates on their position, velocity, and trajectory at a minimum rate of 10 Hz.Comment about deliverable:Frequent updates enable timely decision-making for collision avoidance. During RFQ and for kick off meeting: supplier conformity commitment During development: conformity validated | [2024/03/26] The document MAT1 has been cancelled based on "DML_00123_45_6677_DML_DRONES-2026.xlsx" (version 10.0) from the original .zip file package. | 27/03/2024_RM : To be verified. 01/08/2024_RM : Not Applicable. Closed. | Not applicable | Closed |  |  | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_020 B | OBS_06 | The object tracking system shall maintain object identity for a minimum of 30 seconds after the object leaves the sensor's field of view, assuming the object's trajectory remains predictable.Milestone: Kick off meeting Comment about deliverable:This requirement supports consistent tracking in cases of temporary occlusion. | [2024/03/26] The document DIAGFR12 is not available in any package for DRONESand not mentioned in any DML for DRONES. | 27/03/2024_RM : To be verified 31/10/2023_BM : OK 01/08/2024_RM : To be verified internally. | Not applicable | In Progress |  |  | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_025 B | OBS_07 | The object detection and tracking system shall achieve a minimum accuracy of 95% for objects larger than 1 cubic meter within 50 meters of the drone.Milestone: Kick off meeting Comment about deliverable: | [2024/03/26] The document DIAGCR12 is not available in any package for DRONESand not mentioned in any DML for DRONES. | 27/03/2024_RM : To be verified 31/10/2023_BM : OK 01/08/2024_RM : To be verified internally. | Not applicable | In Progress |  |  | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_039 | BVLOS_03 | The system shall detect and map static obstacles such as buildings, towers, and terrain features, incorporating them into the navigation planning system. Theme: Validation Milestone: Kick off meeting Comment about deliverable:15/07/2023:The system shall detect and map static obstacles such as buildings, towers, and terrain features, incorporating them into the navigation planning system. | RFQ: Please check DML for the specific response | 27/09/2023: SUPPLIER XYZ should change status to agreed ,already accpted in DML. | In Progress | In Progress |  | IT&V_DRONES | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_040 B | BVLOS_04 | The system shall detect and map static obstacles such as buildings, towers, and terrain features, incorporating them into the navigation planning system. Theme: Validation Milestone: Kick off meeting Comment about deliverable: | RFQ: Please check DML for the specific response | 27/09/2023: SUPPLIER XYZ should change status to agreed ,already accpted in DML. | In Progress | In Progress |  | PM | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_044 | PERF_07 | The system shall incorporate real-time airspace restriction data, including temporary flight restrictions (TFRs) and controlled airspace boundaries, treating them as virtual obstacles in the navigation system. Theme: Validation Milestone: Kick off meeting Comment about deliverable: | RFQ: Please check DML for the specific response | 27/09/2023: SUPPLIER XYZ should change status to agreed ,already accpted in DML. | In Progress | In Progress |  | PM, VSE | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_046 | AUVD_03 | The navigation system shall utilize GPS, GLONASS, and Galileo satellite systems, with RTK corrections when available, to achieve a horizontal position accuracy of ±10 cm in open sky conditions. Theme: Downloading Milestone: Each SW delivery Comment about deliverable: | RFQ: SUPPLIER XYZ delivers SW in standard vector format VBF, which contains hex data | 13/03/2024 : To be discussed with SUPPLIER XYZ. 01/08/2024_RM : Requirement to be converged ASAP. Only .ULP and .CAL are acceptable for COMPANY A. | In Progress | In Progress |  | PM, SW_DRONES | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_047 | AV-DRFC-FUSE-0007 | In GPS-denied environments, the system shall switch to visual-inertial odometry and SLAM techniques, maintaining a position accuracy of ±1 meter for up to 10 minutes of GPS signal loss Theme: Delivery Milestone: Kick off meeting Comment about deliverable: | RFQ: Re-applications quoted seperately | 27/09/2023 : To be discuss with SUPPLIER XYZ | In Progress | In Progress |  | PM, SW_DRONES | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_049 | AV-DRFC-FUSE-0006 | The path planning system shall generate optimal flight paths considering factors such as obstacles, airspace restrictions, wind conditions, and energy efficiency. Milestone: Kick off meeting Comment about deliverable: | [31-05-2024 SYS Drone A] " Comments form SW "On Hold - Tsync strategy not clear, SomeIP starategy not clear awaiting customer(COMPANY A) clarification on above topic." | 27/09/2023:SUPPLIER XYZ should change the status to 'NA' | Not applicable | Closed |  | SYS_DRONES, SW_DRONES | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_050 | AV-SPPC-NAV 51 | The system shall be capable of real-time path replanning at a minimum frequency of 1 Hz to adapt to dynamic obstacles or changing mission parameters.Milestone: Validation phases (see tab "Validation milestones") Comment about deliverable: | [PR_DRONE_AA_2024_04_17] Not applicable based on SQM01 | 06/06/2024_HA : Requirements that are related to harness connector in SQM 01 are not applicable because harness connector was chosen by Stellantis 25/04/2024_HA : SQM01 based on previous Status from RFQ said that is not Applicable TBC internally | Not applicable | Closed |  | PTV_drone, ME_DRONES | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_051 | AV-SPPC-NAV 47 | The navigation system shall enforce both hard and soft geofences. Hard geofences must never be violated, while soft geofences may be crossed with explicit operator authorization. Milestone: IOD Comment about deliverable: | [PR_DRONE_AA_2024_04_18] Based on SQM01_20417_23_00968_GEED_DRONESthe requirement is not applicable, requirement is for connector harness - SUPPLIER XYZ is not responsible for harness/wire | 06/06/2024_HA : Requirements that are related to harness connector in SQM 01 are not applicable because harness connector was chosen by Stellantis 25/04/2024_HA : SQM01 based on previous Status from RFQ said that is not Applicable and SUPPLIER XYZ is not responsible for connector harness TBC internally | Not applicable | Closed |  | PM, ME_DRONES | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_052 | AV-SPPC-NAV 46 | The system shall continuously monitor local weather conditions including wind speed, precipitation, and temperature, using onboard sensors and data links to weather services.Milestone: DFE Comment about deliverable: | [PR_DRONE_AA_2024_04_18] Based on SQM01_20417_23_00968_GEED_DRONESthe requirement is not applicable, requirement is for connector harness - SUPPLIER XYZ is not responsible for harness/wire | 06/06/2024_HA : Requirements that are related to harness connector in SQM 01 are not applicable because harness connector was chosen by Stellantis 25/04/2024_HA : SQM01 based on previous Status from RFQ said that is not Applicable and SUPPLIER XYZ is not responsible for connector harness TBC internally | Not applicable | Closed |  | PM, ME_DRONES | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_053 | AV-SPPC-NAV 19 | The navigation system shall automatically adjust flight parameters and paths based on current and forecasted weather conditions to maintain safe and stable flight. Theme: Milestone: Pilot validation to serial validation Comment about deliverable: | [PR_DRONE_AA_2024_04_18] Based on SQM01_20417_23_00968_GEED_DRONESthe requirement is not applicable, requirement is for connector harness - SUPPLIER XYZ is not responsible for harness/wire | 06/06/2024_HA : Requirements that are related to harness connector in SQM 01 are not applicable because harness connector was chosen by Stellantis 25/04/2024_HA : SQM01 based on previous Status from RFQ said that is not Applicable and SUPPLIER XYZ is not responsible for connector harness TBC internally | Not applicable | Closed |  | PM, ME_DRONES, PTV_drone | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_058 B | AV-DRFC-FUSE-0013 | In low-altitude flights, the system shall maintain a configurable above-ground-level (AGL) altitude, automatically adjusting to follow terrain contours while avoiding obstacles.Milestone: DFE Comment about deliverable: | [PR_DRONE_AA_2024_04_18] Based on SQM01_20417_23_00968_GEED_DRONESthe requirement is not applicable, requirement is for connector harness - SUPPLIER XYZ is not responsible for harness/wire | 06/06/2024_HA : Requirements that are related to harness connector in SQM 01 are not applicable because harness connector was chosen by Stellantis 25/04/2024_HA : SQM01 based on previous Status from RFQ said that is not Applicable and SUPPLIER XYZ is not responsible for connector harness TBC internally | Not applicable | Closed |  | ME_DRONES, SYS_DRONES, SW_DRONES | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_061 | AV-SPPC-NAV 53 | The system shall include noise reduction flight modes, automatically activating when flying over noise-sensitive areas as defined in its geographical database. Milestone: DFE Comment about deliverable: | [PR_DRONE_AA_2024_04_18] Based on SQM01_20417_23_00968_GEED_DRONESthe requirement is not applicable, requirement is for connector harness - SUPPLIER XYZ is not responsible for harness/wire | 06/06/2024_HA : Requirements that are related to harness connector in SQM 01 are not applicable because harness connector was chosen by Stellantis 25/04/2024_HA : SQM01 based on previous Status from RFQ said that is not Applicable and SUPPLIER XYZ is not responsible for connector harness TBC internally | Not applicable | Closed |  | PM, ME_DRONES | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_205 | AV-SPPC-NAV 18 | The navigation system shall optimize flight paths to minimize energy consumption and emissions, balancing this objective with mission requirements and safety considerations. Theme: Milestone: Tous Comment about deliverable: | [PR_DRONE_AA_2024_04_18] Based on SQM01_20417_23_00968_GEED_DRONESthe requirement is not applicable, requirement is for connector harness - SUPPLIER XYZ is not responsible for harness/wire | 06/06/2024_HA : Requirements that are related to harness connector in SQM 01 are not applicable because harness connector was chosen by Stellantis 25/04/2024_HA : SQM01 based on previous Status from RFQ said that is not Applicable and SUPPLIER XYZ is not responsible for connector harness TBC internally | Not applicable | Closed |  | PM, ME_DRONES | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_206 | AV-SPPC-NAV 03 | The system shall be capable of identifying and avoiding protected wildlife areas and habitats based on a regularly updated geographical database. Theme :Plan Milestone: RFQ Comment about deliverable: | [PR_DRONE_AA_2024_04_18] Based on SQM01_20417_23_00968_GEED_DRONESthe requirement is not applicable, requirement is for connector harness - SUPPLIER XYZ is not responsible for harness/wire | 06/06/2024_HA : Requirements that are related to harness connector in SQM 01 are not applicable because harness connector was chosen by Stellantis 25/04/2024_HA : SQM01 based on previous Status from RFQ said that is not Applicable and SUPPLIER XYZ is not responsible for connector harness TBC internally | Not applicable | Closed |  | ME_DRONES | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_043 | AV-SPPC-NAV 40 | The drone shall be equipped with a biodegradable confetti system for emergency landings in water, aiding in quick location and recovery while minimizing environmental impact.Milestone: IOD Comment about deliverable: | [PR_DRONE_AA_2024_04_18] Based on SQM01_20417_23_00968_GEED_DRONESthe requirement is not applicable, requirement is for connector harness - SUPPLIER XYZ is not responsible for harness/wire | 06/06/2024_HA : Requirements that are related to harness connector in SQM 01 are not applicable because harness connector was chosen by Stellantis 25/04/2024_HA : SQM01 based on previous Status from RFQ said that is not Applicable and SUPPLIER XYZ is not responsible for connector harness TBC internally | Not applicable | Closed |  | PM, ME_DRONES | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_207 | AV-DRFC-FUSE-0011 | The navigation system shall include "eco-flight" modes that prioritize energy efficiency and minimal environmental impact, even if it results in longer flight times. Theme: Plan Milestone: TOP DFE Comment about deliverable: | [PR_DRONE_AA_2024_04_18] Based on SQM01_20417_23_00968_GEED_DRONESthe requirement is not applicable, requirement is for connector harness - SUPPLIER XYZ is not responsible for harness/wire | 06/06/2024_HA : Requirements that are related to harness connector in SQM 01 are not applicable because harness connector was chosen by Stellantis 02/05/2024_HA : SQM01 based on previous Status from RFQ said that is not Applicable and SUPPLIER XYZ is not responsible for connector harness TBC internally | Not applicable | Closed |  | ME_DRONES | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_208 | AV-DRFC-FUSE-0008 | The system shall continuously evaluate mission objectives against current environmental conditions and autonomously propose mission adjustments to the operator when original objectives become unfeasible or high-risk. Theme: Plan Milestone: DFE Comment about deliverable: | [PR_DRONE_AA_2024_04_18] Based on SQM01_20417_23_00968_GEED_DRONESthe requirement is not applicable, requirement is for connector harness - SUPPLIER XYZ is not responsible for harness/wire | 06/06/2024_HA : Requirements that are related to harness connector in SQM 01 are not applicable because harness connector was chosen by Stellantis 25/04/2024_HA : SQM01 based on previous Status from RFQ said that is not Applicable and SUPPLIER XYZ is not responsible for connector harness TBC internally | Not applicable | Closed |  | ME_DRONES | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_098 | AV-SPPC-NAV 12 | The system shall be capable of autonomous return-to-home (RTH) decision making, considering factors such as battery level, weather conditions, and distance to home location.Theme: Plan Milestone: DFE Comment about deliverable: | [PR_DRONE_AA_2024_04_18] Based on SQM01_20417_23_00968_GEED_DRONESthe requirement is not applicable, requirement is for connector harness - SUPPLIER XYZ is not responsible for harness/wire | 06/06/2024_HA : Requirements that are related to harness connector in SQM 01 are not applicable because harness connector was chosen by Stellantis 02/05/2024_HA : SQM01 based on previous Status from RFQ said that is not Applicable and SUPPLIER XYZ is not responsible for connector harness TBC internally | Not applicable | Closed |  | ME_DRONES | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_099 | EE-CPPC-CON 43 | In multi-drone operations, the system shall dynamically adjust individual drone paths to optimize overall mission objectives while maintaining safe separation distances between drones. Theme: Milestone: RFQ Comment about deliverable: | [PR_DRONE_AA_2024_04_18] Based on SQM01_20417_23_00968_GEED_DRONESthe requirement is not applicable, requirement is for connector harness - SUPPLIER XYZ is not responsible for harness/wire | 06/06/2024_HA : Requirements that are related to harness connector in SQM 01 are not applicable because harness connector was chosen by Stellantis 25/04/2024_HA : SQM01 based on previous Status from RFQ said that is not Applicable and SUPPLIER XYZ is not responsible for connector harness TBC internally | Not applicable | Closed |  | ME_DRONES | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ_062 B | AV-SPPC-NAV 39 | The navigation system shall include an adaptive learning component that improves path planning efficiency based on data from previous missions in similar environments or conditions. Milestone: IOD Comment about deliverable: | [PR_DRONE_AA_2024_04_18] Based on SQM01_20417_23_00968_GEED_DRONESthe requirement is not applicable, requirement is for connector harness - SUPPLIER XYZ is not responsible for harness/wire | 06/06/2024_HA : Requirements that are related to harness connector in SQM 01 are not applicable because harness connector was chosen by Stellantis 25/04/2024_HA : SQM01 based on previous Status from RFQ said that is not Applicable and SUPPLIER XYZ is not responsible for connector harness TBC internally | Not applicable | Closed |  | PM, ME_DRONES | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ-0700301 A | AV-SPPC-NAV 50 | The function NA01 - Drone Path Predictor shall use the LEGACY_PATH Message which contains at least the following attributes: Path Segment ID, LegacyPathSegmentIdByNav Segment Length, LegacySegmentLengthByNav Terrain Type, LegacyTerrainTypeByNav Obstacle Density, LegacyObstacleDensityByNav Wind Factor, LegacyWindFactorByNavMilestone: DFE Comment about deliverable: | [PR_DRONE_AA_2024_04_18] Based on SQM01_20417_23_00968_GEED_DRONESthe requirement is not applicable, requirement is for connector harness - SUPPLIER XYZ is not responsible for harness/wire | 06/06/2024_HA : Requirements that are related to harness connector in SQM 01 are not applicable because harness connector was chosen by Stellantis 25/04/2024_HA : SQM01 based on previous Status from RFQ said that is not Applicable and SUPPLIER XYZ is not responsible for connector harness TBC internally | Not applicable | Closed |  | PM, ME_DRONES | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ-0700302 B | AV-SPPC-NAV 51 | The function NA01 - Drone Path Predictor shall extract available attributes from LEGACY_PATH message to provide the following related attributes: Segment ID, DronePathSegmentId Segment Length, DronePathSegmentLength Terrain Classification, DronePathTerrainClass Obstacle Index, DronePathObstacleIdx Wind Correction Factor, DronePathWindCorrection For R25 and higher: Path Confidence Level, DronePathConfidenceLevel Energy Consumption Estimate, DronePathEnergyEstimate Theme: Plan Milestone: DFE Comment about deliverable: | [PR_DRONE_AA_2024_04_18] Based on SQM01_20417_23_00968_GEED_DRONESthe requirement is not applicable, requirement is for connector harness - SUPPLIER XYZ is not responsible for harness/wire | 06/06/2024_HA : Requirements that are related to harness connector in SQM 01 are not applicable because harness connector was chosen by Stellantis 25/04/2024_HA : SQM01 based on previous Status from RFQ said that is not Applicable and SUPPLIER XYZ is not responsible for connector harness TBC internally | Not applicable | Closed |  | ME_DRONES | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements
REQ-0700401 C | AV-SPPC-NAV 52 | The function EM01 - Environmental Monitor shall utilize the DEPRECATED_WEATHER_DATA input which includes the following parameters: Temperature, DeprecatedTempByWeather Humidity, DeprecatedHumidByWeather Wind Speed, DeprecatedWindSpeedByWeather Wind Direction, DeprecatedWindDirByWeather Precipitation Probability, DeprecatedPrecipProbByWeather The function shall process this data to output: Current Weather Condition, DroneEnvWeatherCondition Flight Risk Level, DroneEnvFlightRiskLevel Recommended Speed Adjustment, DroneEnvSpeedAdjust. Theme: Milestone: TOP DFE Comment about deliverable: | [PR_DRONE_AA_2024_04_18] Based on SQM01_20417_23_00968_GEED_DRONESthe requirement is not applicable, requirement is for connector harness - SUPPLIER XYZ is not responsible for harness/wire | 06/06/2024_HA : Requirements that are related to harness connector in SQM 01 are not applicable because harness connector was chosen by Stellantis 25/04/2024_HA : SQM01 based on previous Status from RFQ said that is not Applicable and SUPPLIER XYZ is not responsible for connector harness TBC internally | Not applicable | Closed |  | PM, ME_DRONES | Stakeholder Requirement | FEA05_01234_23_03456_autonomous_drone_navigation_requirements